## Summary
ATOM Feature Audit Tracker
Goal | Audit every feature, define user stories, test, fix logistical/UX errors, and retest.
Canonical status | Complete
Stories tracked | 28
Errors documented | 5
Errors fixed | 5
Final pytest | 189 passed in 35.17s
Supplemental smokes | Solver docs, descriptors, data pipeline, dashboard notebook, EXX/RPA, ML-XC dummy calculator
Workbook generated | 2026-06-21
Status | Count | Error Status | Count
Passed | 28 | Fixed | 5
Failed | 0 | Open | 0
Fixed stories | 6 | Total | 5
Total | 28

## User Stories
ID | Feature Area | User Story | Expected Behavior | Evidence | Test Method | Initial Status | Errors Found | Fix Applied | Post-Fix Status | Notes
F001 | Install and import | As a researcher, I can install the core package and import the public solver. | Core install exposes atom.AtomicDFTSolver and imports without optional extras. | README.md; pyproject.toml; atom/__init__.py | Import smoke | Passed | None | N/A | Passed | Smoke printed atom import OK.
F002 | Development setup | As a contributor, I can install the dev extra and run tests. | The dev extra includes all packages needed for pytest collection, including plotting imports used by tests. | pyproject.toml; tests/__init__.py; tests/solver_basic_testcase.py | Initial pytest + post-fix pytest | Failed | ERR-001 | Added matplotlib to dev extra. | Passed | 189 passed in 35.17s after fix.
F003 | Documentation examples | As a new user, I can copy solver snippets from intro/tutorial/cookbook/API docs. | Docs use finite_element_number and dictionary result keys returned by solve(). | docs/intro.md; docs/tutorials/01_basic_solver.md; docs/cookbook.md; docs/api/reference.md | Doc search + solver smoke | Failed | ERR-002 | Updated stale object-style result access and old parameter names. | Passed | Corrected snippets smoke-tested with compact solver.
F004 | Solver initialization | As a solver user, I get validated defaults and clear errors for invalid inputs. | AtomicDFTSolver validates atom, electron count, mesh, quadrature, XC, OEP, ML, and descriptor inputs. | atom/solver.py | pytest + smoke | Passed | None | N/A | Passed | Covered by solver and descriptor contract tests.
F005 | Basic all-electron solve | As a user, I can solve small all-electron atoms with LDA/GGA and inspect energy, density, orbitals, and convergence. | solve() returns a dictionary with energy, rho, orbitals, converged, iterations, residual, grids, potentials, and energy components. | atom/solver.py; docs/tutorials/01_basic_solver.md | pytest + compact solver smoke | Passed | None | N/A | Passed | LDA_PW and GGA_PBE compact smokes converged.
F006 | Pseudopotential workflow | As a user, I can run pseudopotential calculations when psp8 files are available. | LocalPseudopotential loads psp8 data and solver defaults use psps/XX.psp8 for pseudopotential mode. | atom/pseudo/local.py; atom/pseudo/read_pseudopotential.py; psps/ | Parser smoke + pytest | Passed | None | N/A | Passed | psps/01.psp8 parsed; pytest exercises PSP-aware dashboard state.
F007 | Custom mesh and quadrature | As a numerical user, I can tune domain, finite elements, polynomial order, quadrature, and mesh type. | Mesh1D and RadialOperatorsBuilder produce valid radial nodes and FE operators. | atom/mesh/builder.py; atom/mesh/operators.py | pytest + mesh smoke | Passed | None | N/A | Passed | Quadrature, mesh nodes, and shape functions smoke-tested.
F008 | SCF debug outputs | As a user diagnosing convergence, I can request intermediate iteration data, energy density, and full spectrum outputs. | solve(save_intermediate, save_energy_density, save_full_spectrum) includes intermediate_info, e_x/e_c, and full eigen arrays. | atom/solver.py; atom/scf/driver.py | pytest + compact solver smoke | Passed | None | N/A | Passed | Full spectrum and intermediate paths smoke-tested.
F009 | Initial density and interpolation | As an advanced user, I can provide rho_initial and evaluate fields on the output uniform grid. | solve accepts rho_initial with shape checks; evaluate_single_field_on_grid interpolates quadrature fields. | atom/solver.py; atom/mesh/operators.py | Smoke | Passed | None | N/A | Passed | rho_initial and uniform-grid interpolation smoke-tested.
F010 | XC functional registry | As a method developer, I can inspect functional requirements and registered functionals. | Registry exposes LDA, GGA, meta-GGA, hybrid, EXX, RPA, and None requirements. | atom/xc/functional_requirements.py | Smoke + pytest | Passed | None | N/A | Passed | list_available_functionals and SCAN requirements smoke-tested.
F011 | Meta-GGA workflows | As a user, I can use SCAN-family functionals that need gradients and kinetic energy density. | SCAN/RSCAN/R2SCAN requirements include tau and Hamiltonian cache remains stable. | atom/xc/meta_scan.py; atom/scf/hamiltonian.py | pytest + compact SCAN smoke | Passed | None | N/A | Passed | Compact SCAN returned finite result; full tests cover cache/idempotence.
F012 | Hybrid exchange | As a user, I can solve with PBE0/HF-style exact exchange components. | PBE0 uses hybrid exchange and returns local exchange/correlation potentials. | atom/xc/hf.py; atom/scf/energy.py | pytest + compact PBE0 smoke | Passed | None | N/A | Passed | PBE0 end-to-end tests and compact smoke passed.
F013 | OEP/EXX workflow | As an advanced user, I can run OEP-enabled EXX calculations. | EXX requires OEP and returns finite density/orbitals/energy under compact smoke settings. | atom/xc/oep.py; atom/solver.py | Compact advanced smoke | Passed | None | N/A | Passed | Finite EXX smoke passed; low outer-iteration smoke did not require convergence.
F014 | RPA workflow | As an advanced user, I can run RPA correlation calculations. | RPA uses response/frequency grids and returns finite density/orbitals/energy under compact smoke settings. | atom/xc/rpa.py; atom/scf/response.py; atom/mesh/builder.py | Compact advanced smoke | Passed | None | N/A | Passed | Finite RPA smoke passed with small quadrature; runtime warnings noted but no failure.
F015 | SCF result serialization | As a tooling user, I can serialize and restore SCFResult objects and legacy key names. | SCFResult.to_dict/from_dict preserve current names and accept legacy names. | atom/scf/driver.py | pytest | Passed | None | N/A | Passed | Serialization tests passed.
F016 | Descriptor API validation | As a descriptor user, invalid multipole configs fail early with clear errors. | MultipoleCalculator validates angular basis, radial basis, rcuts, l_max, spacing, box size, periodic, and name. | atom/descriptors/calculator.py; atom/descriptors/kernels.py | pytest | Passed | None | N/A | Passed | Validation tests passed.
F017 | Radial multipole descriptors | As an ML-XC researcher, I can compute Heaviside and Legendre MCSH descriptors from radial density. | compute_from_radial projects radial density to 3D and returns MultipoleResult with descriptor tensor metadata. | atom/descriptors/calculator.py; atom/descriptors/multipole.py | pytest + smoke | Passed | None | N/A | Passed | Legendre and Heaviside radial descriptor tests passed.
F018 | 3D multipole descriptors | As a descriptor user, I can compute descriptors from 3D density grids and extract radial profiles. | compute_from_3d supports eval_indices, center, periodic mode, and radial profile extraction. | atom/descriptors/calculator.py; atom/descriptors/grid3d.py | pytest + smoke | Passed | None | N/A | Passed | 3D descriptor and profile tests passed.
F019 | Inline solver descriptors | As a solver user, I can attach descriptor calculators to solve() and receive descriptor_results without changing SCF. | AtomicDFTSolver runs DescriptorCalculator instances after SCF and keys results by calculator.name. | atom/solver.py; atom/descriptors/base.py | pytest + inline smoke | Passed | None | N/A | Passed | Inline descriptor smoke produced tensor shape (9, 1, 2).
F020 | Descriptor utility IO | As a data user, I can normalize radial densities and write/read cube files or NPZ descriptor files. | Density helpers normalize distributions; grid3d writes/reads Gaussian cube; MultipoleResult.to_npz exports descriptor arrays. | atom/descriptors/density.py; atom/descriptors/grid3d.py; atom/descriptors/multipole.py | Smoke + new pytest | Failed | ERR-004 | Replaced np.trapz call with np.trapezoid fallback and added regression test. | Passed | New density helper test passed; smoke covered cube and NPZ IO.
F021 | MCSH scientific validation | As a researcher, I can trust descriptor invariants across atoms and kernels. | Validation tests cover charge sum rule, dipole vanishing, monotonicity, LP0 identity, Legendre diversity, and master parity. | tests/test_mcsh_multi_atom_validation.py; tests/test_multipole_master_parity.py | pytest | Passed | None | N/A | Passed | Included in 189-test pass.
F022 | Data generation and loading | As an ML data user, I can generate a small dataset and load selected features. | AtomicDataManager coordinates DataGenerator, DataLoader, and DataProcessor for configuration folders. | atom/data/data_manager.py; atom/data/data_generation.py; atom/data/data_loading.py | Temp-directory data smoke | Passed | None | N/A | Passed | Generated and loaded one H/GGA_PBE configuration.
F023 | Data processing transforms | As a data user, I can apply symlog/symexp transforms and weights. | DataProcessor exposes reversible symlog/symexp and weighting helpers. | atom/data/data_processing.py | Smoke | Passed | None | N/A | Passed | symlog/symexp round-trip smoke passed.
F024 | Visualization utilities | As an analyst, I can import plotting utilities when matplotlib is installed. | DataVisualizer and notebook dashboard rely on matplotlib; dev extra now supplies it for tests. | atom/data/data_visualization.py; atom/ui/notebook_dashboard.py; pyproject.toml | Import/pytest | Failed | ERR-001; ERR-003 | Added matplotlib to dev and fixed dashboard install hint. | Passed | Dashboard tests and notebook execution passed.
F025 | ML-XC calculator plumbing | As an ML-XC developer, I can construct a model-backed calculator from a class and make potential predictions. | XCBaseModel supports model_cls construction without requiring model_dir; MLXCCalculator wraps feature transforms and predictions. | atom/xc/ml_xc/base.py; atom/xc/ml_xc/calculator.py | Dummy-model smoke + new pytest | Failed | ERR-005 | Stored model_dir as None when not supplied and added regression test. | Passed | Dummy calculator prediction passed; full Torch training not run without optional ml extra.
F026 | Notebook dashboard controls | As a notebook user, I can configure runs, queue jobs, restrict missing PSPs, compute/export descriptors, and see status. | AtomDFTDashboard snapshots widget state and exports descriptor metadata from completed jobs. | atom/ui/notebook_dashboard.py; tests/test_notebook_dashboard.py | pytest | Passed | None | N/A | Passed | Dashboard unit tests passed.
F027 | Dashboard notebook startup | As a notebook user, I can open and execute the dashboard notebook cell. | notebooks/atom_dft_dashboard.ipynb imports AtomDFTDashboard and builds widgets. | notebooks/atom_dft_dashboard.ipynb; atom/ui/notebook_dashboard.py | nbconvert execution | Passed | None | N/A | Passed | Executed notebook had zero cell errors.
F028 | Docs and release site source | As a documentation user, source docs align with the current package API. | Docs describe current solver keyword names and result dictionary keys. | docs/intro.md; docs/cookbook.md; docs/tutorials/01_basic_solver.md; docs/api/reference.md | Doc search + smoke | Failed | ERR-002 | Patched docs to current API. | Passed | No stale result object patterns remain in source docs.

## Errors
ID | Type | Observed Error | Evidence | Fix Applied | Status | Retest Evidence
ERR-001 | Logistical | pytest collection failed after installing .[dev] because tests import matplotlib but dev extra omitted it. | pyproject.toml dev extra | Add matplotlib>=3.3.0 to dev dependencies. | Fixed | pytest collected and passed 189 tests.
ERR-002 | UX docs | Intro/tutorial/cookbook/API docs used stale finite_elements keyword and result.total_energy/result.density object access. | docs/intro.md; docs/tutorials/01_basic_solver.md; docs/cookbook.md; docs/api/reference.md | Update examples to finite_element_number and result[...] dictionary keys. | Fixed | Doc search clean; compact solver snippet smoke passed.
ERR-003 | UX install hint | Dashboard ImportError suggested pip install -e '.[dev,viz]' even though dev now covers notebook/test plotting needs. | atom/ui/notebook_dashboard.py | Update message to pip install -e '.[dev]'. | Fixed | Dashboard tests and notebook execution passed.
ERR-004 | Compatibility | normalize_density used np.trapz, unavailable in NumPy 2.4 installed by declared numpy>=1.20 range. | atom/descriptors/density.py | Use np.trapezoid when available with np.trapz fallback; add regression test. | Fixed | test_descriptor_density_helpers.py passed; full suite passed.
ERR-005 | ML-XC constructor | XCBaseModel from-class path accepted no model_dir but unconditionally called Path(None). | atom/xc/ml_xc/base.py | Store None when model_dir is omitted; add dummy-model regression test. | Fixed | test_ml_xc_calculator.py passed; full suite passed.

## Test Runs
ID | Scope | Command or Method | Status | Result | Notes
TR-001 | Initial pytest with system Python | python3 -m pytest -q | Failed | No module named pytest | Used temp uv environment for repeatable testing.
TR-002 | Initial pytest with .[dev] before fix | /tmp/atom-dft-mlxc-testenv/bin/python -m pytest -q | Failed | 13 collection errors: ModuleNotFoundError matplotlib | Led to ERR-001.
TR-003 | Post dependency fix pytest | /tmp/atom-dft-mlxc-testenv/bin/python -m pytest -q | Passed | 187 passed in 42.54s | Confirmed metadata fix.
TR-004 | Corrected solver docs smoke | Compact AtomicDFTSolver snippets | Passed | LDA_PW compact solve converged and printed dict-key values | Validated docs result access.
TR-005 | Inline descriptor smoke | AtomicDFTSolver(... descriptor_calculators=[MultipoleCalculator]) | Passed | Descriptor tensor shape (9, 1, 2) | Validated user-facing descriptor integration.
TR-006 | Broad story smoke | Utilities, mesh, pseudopotential parser, descriptors, cube IO, compact solver modes, rho_initial | Passed | ALL STORY SMOKES PASSED | Found ERR-004 before passing.
TR-007 | Data pipeline smoke | AtomicDataManager generate_data/load_data in temp dir | Passed | Generated and loaded one configuration | Validated data workflow without persistent files.
TR-008 | Dashboard notebook execution | jupyter nbconvert --execute notebooks/atom_dft_dashboard.ipynb | Passed | 0 cell errors | Validated notebook startup.
TR-009 | Advanced EXX/RPA compact smoke | EXX and RPA compact finite-result solves | Passed | Finite energies; no convergence required under 3 outer iterations | Validated advanced paths at smoke level.
TR-010 | ML-XC dummy calculator smoke | Dummy XCBaseModel + MLXCCalculator.predict_vxc | Passed | Predictions [1.0, 2.0] | Found ERR-005 before passing.
TR-011 | New regression tests | pytest tests/test_descriptor_density_helpers.py tests/test_ml_xc_calculator.py | Passed | 2 passed in 0.34s | Validated new bug fixes.
TR-012 | Final full pytest | /tmp/atom-dft-mlxc-testenv/bin/python -m pytest -q | Passed | 189 passed in 35.17s | Final post-fix suite.